## Sheet1
Iteration 1 8/6/2012 | Notes
Home Page
Basic Search
Login
Profile
Q&A
Moderation Tool
Blog/Buy Guide
Customer Service Page
Social Share
Experts & Badging
Comments
Google Analytics
Iteration 2 8/27/2012
Migration
Following
Omniture Integration
Iteration 3 9/17/2012
Enhance CMS
Category Page Templates
Email Notifications
Iteration 4 10/8/2012
Ad Units
Voting and Flagging
Reporting
Iteration 5 10/24/2012
Smart Search
Add Manuals
Ability to Syndicate Q&A Widget to core sites
Backlog
Polls