## Sheet1
Site | Version of WP | Order to Convert | Tested up to | Risk | Comment | Test Time
David Tutera | 3.0.1 | 1 | - | L | - | 8
UXBlog | - | 2 | - | L | - | 16
Gamer | 3.1.3 | 3 | - | L | - | 8
MyGofer Blog | 3.0.1 | 4 | - | L | - | 8
Grilling is Happiness | - | 5 | 3.3.1 | M | Admin issue | 16
StyleSip Fashion | 3.1 | 6 | 3.3.1 | M | - | 8
Birthday Club | 3.1.3 | 8 | 3.3.1 | H | - | 16
Kmart Fashion | 3.1.3 | 7 | 3.3.1 | H | - | 24
Playdate Place | 3.0.1 | 9 | - | M | - | 24
FitStudio Blog | 3.0.1 | 79 | - | M | - | 16
Fitstudio Gear | 3.1.3 | 80 | - | H | waiting for agilysis launch | 32
Handbooks | 3.1 | 89 | - | H | 1st custom post type. Need estimate to convert theme | 32
SUWYG | - | 99 | 3.3.1 | M | Launch May 8th | 8
ODL Sears | - | 99 | 3.3.1 | L | Launch June 1 | 8
ODL Kmart | - | 99 | 3.3.1 | L | TBD | 8
Kitson | - | 99 | 3.3.1 | L | TBD | 8
People’s Pick | 3.2.1 | n/a | n/a | L | - | 0