## Sheet1
Web Development | Duration | Contact | Jira Link | Comments
Kickoff Meeting | 1 day
DNS | 1-5 days? | Linda Devlin
If available, check for a trademark search to clear the domain name for use of registration |  |  |  | • Advice how the business plans to use the domain name (e.g., redirect to sears.com or kmart.com, or point to a new website, etc.) • If it's new website, associates should describe any goods and services that will be offered on the site
If no trademark search is needed, register the domain name by contacting CSC | 1 day | Linda will contact CSC Corporate Domains, requesting they register the domain name
If trademark search is needed, contact trademark paralegal to have the term in the domain name searched | 1 week | Linda will contact Laura Well (trademark paralegal)
If the search show that the term in the domain name is clear for use and registration, register the domain name by contacting CSC
Archetecture/Environment
Set up DNS | ? | ? |  | Simulteneously with Wire designs. Depend on URL purchase
Open Jira for Vanity URL |  | obu_os_devops@searshc.com | https://jira.intra.sears.com/jira/browse/ESOC-40222
UX (wires) | 1.5-5 weeks |  |  | Simulteneously with DNS setup. Really depends on size of the PRD (requirements),if there is no client involvement 2 weeks for full size project that would otherwise take 5 weeks
Wires Signoff | 1 day
Creative (designs) | 1-2 weeks |  |  | Dependency: Full annotated Wires. 2 weeks for full site design
Creative signoff | 1 day
Dev/Build
Front End Dev |  |  |  | Dependent on wires and comps
CMS |  |  |  | If building on Wordpress, we don’t need to build time because its built in
API
Crons/Infrastructure | 5 days |  |  | Acquiring server and databases
Server Middleware