## Sheet1
Task | Hours | Sub-Total
Coding
Blogging | 40
Taxonomy | 40
Comments | 10
Social Media Integration | 20
Background Images | 20 |  | This is similar to sears.com/outdoorstyle
Hero Image Carousel | 40
YouTube Videos | 10
Search | 10
Featured Posts | 20
210
Theme Development
Theme | 160 |  | Explained that we needed this to move off of thematic.
Kmart Header/Footer | 40
200
Server Management
Set-up | 20
Database | 10
Domain setup | 30
60
Knowledge Base
Training | 80
80
GRAND TOTAL |  | 550
QA |  | 110
|  | 660 | 4.125
Note: Add 20 hours for ux (meeting on 8-6-12