## Sheet1
Task Name | Duration | Start | Finish | Predecessors
WP upgrade and Install NGINX |  | 2012-05-01
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 5 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security
Launch | 1 day |  |  | 28