## Sheet1
Task Name | Duration | Start | Finish | Predecessors
WP upgrade and Install NGINX |  | Thu 4/12/12 | Fri 4/27/12
Infrastructure | 1 day | Thu 4/12/12 | Thu 4/12/12
WP upgrade | 7 days | Fri 4/13/12 | Fri 4/23/12
Back up existing database | 1 day | Fri 4/13/12 | Fri 4/13/12
Delete current directory | 1 day | Mon 4/16/12 | Mon 4/16/12 | 5
Download and unzip WP into specific path | 1 day | Tue 4/17/12 | Tue 4/17/12 | 6
Configure | 1 day | Wed 4/18/12 | Wed 4/18/12 | 7
Upgrade DB (wp auto-script) | 1 day | Thu 4/19/12 | Thu 4/19/12 | 8
Generic QA plan | 0.5 day | Fri 4/20/12 | Fri 4/20/12
Site Specific QA plan | 0.5 day | Fri 4/20/12 | Fri 4/20/12
QA (basic testing) | 1 day | Mon 4/23/12 | Mon 4/23/12 | 9
Dev Ops | 5 days | Tue 4/24/12 | Fri 4/27/12 | 4
Get apache + mod_ssl installed | 1 day | Wed 4/25/12 | Wed 4/25/12
Move everything over to uxwpress302p-305p running on apache | 1 hr | Thu 4/26/12 | Thu 4/26/12 | 14
As each site is upgraded, shut off apache turn on nginx | 1 day | Fri 4/27/12 | Fri 4/27/12 | 12
Launch | 1 day | Fri 4/27/12 | Fri 4/27/12 | 16