## Parent
Task Name | Duration | Start | Finish | Predecessors
WP upgrade and Install NGINX
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## UXBlog
Task Name | Duration | Start | Finish | Predecessors
UXBLOG | 28 days | 2012-03-23 | 2012-05-01
Infrastructure | 1 day | 2012-03-23 | 2012-03-23
WP upgrade | 5 days | 2012-03-26 | 2012-03-30
Generic QA plan | 1 day
Site Specific QA plan | 3 day
QA (basic testing) | 1 day
SEO Enhancements | 2 1/2 weeks | 2012-04-02 | 2012-04-18
App Development | 3 days | 2012-04-02 | 2012-04-04
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks | 2012-04-05 | 2012-04-18
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days | 2012-04-19 | 2012-04-23 | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 9
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 11
Security | 5 days | 2012-04-24 | 2012-04-30
Launch | 1 day | 2012-05-01 | 2012-05-01 | 12

## David Tutera
Task Name | Duration | Start | Finish | Predecessors
DAVID TUTERA
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## Gamer
Task Name | Duration | Start | Finish | Predecessors
GAMER
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## MyGofer Blog
Task Name | Duration | Start | Finish | Predecessors
MYGOFER BLOG
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## GIH
Task Name | Duration | Start | Finish | Predecessors
GRILLING IS HAPPINESS
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## Stylesip Fashion
Task Name | Duration | Start | Finish | Predecessors
STYLESIP FASHION
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## BDC
Task Name | Duration | Start | Finish | Predecessors
BIRTHDAY CLUB
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## KF
Task Name | Duration | Start | Finish | Predecessors
KMART FASHION
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## Playdate Place
Task Name | Duration | Start | Finish | Predecessors
PLAYDATE PLACE
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## Fitstudio Blog
Task Name | Duration | Start | Finish | Predecessors
FITSTUDIO BLOG
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## Fitstudio Gear
Task Name | Duration | Start | Finish | Predecessors
FITSTUDIO GEAR
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## Handbooks
Task Name | Duration | Start | Finish | Predecessors
HANDBOOKS
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## ODL Sears
Task Name | Duration | Start | Finish | Predecessors
ODL SEARS
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## ODL Kmart
Task Name | Duration | Start | Finish | Predecessors
ODL KMART
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28

## Kitson
Task Name | Duration | Start | Finish | Predecessors
KITSON
Infrastructure | 1 day
WP upgrade | 7 days
Back up existing database | 1 day
Delete current directory | 1 day |  |  | 5
Download and unzip WP into specific path | 1 day |  |  | 6
Configure | 1 day |  |  | 7
Upgrade DB (wp auto-script) | 1 day |  |  | 8
Generic QA plan | 0.5 day
Site Specific QA plan | 0.5 day
QA (basic testing) | 1 day |  |  | 9
SEO Enhancements
App Development
Mitigation
QA
Informing other of dependency
Network Engineer | 2 Weeks
Open VIP
DNS Setup for new URL
Akami ignore rule
Verify
Security audit
Dev Ops | 3 days |  |  | 4
Get apache + mod_ssl installed | 1 day
Move everything over to uxwpress302p-305p running on apache | 1 hr |  |  | 25
As each site is upgraded, shut off apache turn on nginx | 1 day |  |  | 12
Security | 5 days
Launch | 1 day |  |  | 28